|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | **2021-2022** | **Key Players** | **APR 2021** | **MAY 2021** | **JUN 2021** | **JUL 2021** | **AUG 2021** | **SEP 2021** | **OCT 2021** | **NOV 2021** | **DEC 2021** | **JAN 2022** | **FEB 2022** | **MAR 2022** |
| **Key Events** | **AN** |  |  | AN Grand Council and Elections | Proposed AN/CAN Leadership Meeting |  | Possible Federal Election | Proposed AN/CAN Leadership Meeting | AN Grand Council Fall Assembly |  | Proposed AN/Leadership Meeting |  | Proposed AN/CAN Leadership Meeting  Signing Ceremony  Take inventory on who’s in/out  PI/IF Resourcing for Central Body |
| **Ratification Process** | **AN/FNs and Canada** | Ratification Comms Outreach | Ratification Comms Outreach | Ratification Comms Outreach | Ratification vote period-Concludes | Parties meet to discuss vote results. | Parties meet to discuss vote results  Ratification  Comms  Outreach | Ratification  Comms  Outreach | Ratification  Comms  Outreach | Ratification  Comms  Outreach | Ratification  Comms  Outreach | Ratification vote period-Concludes | Parties meet to discuss vote results.  Jointly announce vote result |
| **Pre-Effective Date activities** | **Pre-Implementation Support** | **AN and Canada   Later: Ratifying FNs** |  | Proposal Received.  (Discussion/negotiation – PI/IF for Central Body) |  |  | Confirm Contribution Funding | Ongoing | Ongoing | Ongoing | Ongoing | Ongoing | Ongoing | AN pre implementation ready  PI/IF submission to look at Central Body / AN support and request for assistance |
| **Enabling Legislation** | **AN/FNs and Canada** |  |  | Consultation (draft enabling legislation) | Consultation (draft enabling legislation) | Consultation concluded (draft enabling legislation) | Target to introduce Enabling Legislation – AN communications strategy/plan |  | Support Activities for Bill | Support Activities for Bill | Support Activities for Bill | Support Activities for Bill | Target Royal Assent |
| **Formalize Agreements** | **AN/FNs and Canada** | Notice to FNs on proposed amendments to current funding agreements | Translated ANGA requires confirmation by AN., ANFA, IP to be translated by Canada |  |  |  | Signing of ANGA   Digitizing/HTML coding of ANGA + prepare to post online on the effective date. | Update ANFA | Update ANFA | Update ANFA | Update ANFA | Update ANFA |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | **2022-2023** | **Key Players** | **APR 2022** | **MAY 2022** | **JUN 2022** | **JUL 2022** | **AUG 2022** | **SEP 2022** | **OCT 2022** | **NOV 2022** | **DEC 2022** | **JAN 2023** | **FEB 2023** | **MAR 2023** |
| **Key Events** | **AN** | Future/Comprehensive Negotiations |  | AN Grand Council |  | Appointment of IOC representatives (Canada/FNs) |  |  | AN Grand Council Fall Assembly |  |  |  |  |
| **Ratification Process** | **AN/FNs and Canada** |  |  |  |  |  |  |  | Ratification  Comms  Outreach | Ratification  Comms  Outreach | Ratification  Comms  Outreach | Ratification vote period -Concludes |  |
| **Pre-Effective Date Activities** | **Enabling Legislation** | **Canada**  **TAG &**  **Implementation Sector** |  | Order In Council (OIC) setting effective date |  |  |  |  | Target Effective Date for ANGA and 1st fiscal transfer |  |  |  |  |  |
| **Formalize Agreements** | **AN/FNs and CIRNA/ISC** | Signing: ANFA, IP &  amendments to current funding agreements |  |  |  |  |  |  |  |  |  |  |  |