## General Vote Activities
2 mths Before Vote | 1 mth Before Vote | 1st VOTE | Post-Vote Activities | 2 mths Before Vote | 1 mth Before Vote | 2nd VOTE | Post-Vote Activities
1st VOTE |  |  |  | 2nd VOTE
PRE-VOTE | PRE-VOTE | VOTE | POST VOTE | PRE-VOTE | PRE-VOTE | VOTE | POST VOTE
Hire/Appoint Vote Staff | 30 day deadline | Full Month or as advised by FN | Appeal Period | Hire/Appoint Vote Staff (if appl.) | 30 day deadline | Full Month or as advised by FN | Appeal Period
Train Vote Staff | Notice of Vote |  | 10 day to submit | Train Vote Staff (if appl.) | Notice of Vote |  | 10 day to submit
Prep for deadlines | Post List |  | 14 day to decide | Prep for deadlines | Post List |  | 14 day to decide
| Mail Outs |  |  |  | Mail Outs
| Info Session |  | *60 day post vote activities |  | Info Session |  | *60 day post vote activities

## SEPT 2021 - FEB 2022 1st 2nd
JULY 2021 | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | JANUARY 2022 | FEBRUARY | MARCH | APRIL
1st VOTE |  |  |  | 2nd VOTE
PRE-VOTE | PRE-VOTE | VOTE | POST VOTE | PRE-VOTE | PRE-VOTE | VOTE | POST VOTE
Hire/Appoint Vote Staff | 30 day deadline | Full Month or as advised by FN | Appeal Period | Hire/Appoint Vote Staff (if appl.) | 30 day deadline | Full Month or as advised by FN | Appeal Period
Train Vote Staff | Notice of Vote |  | 10 day to submit | Train Vote Staff (if appl.) | Notice of Vote |  | 10 day to submit
Prep for deadlines | Post List |  | 14 day to decide | Prep for deadlines | Post List |  | 14 day to decide
| Mail Outs |  |  |  | Mail Outs
| Info Session |  | *60 day post vote activities |  | Info Session |  | *60 day post vote activities
| 1st VOTE |  |  |  | 2nd VOTE
| PRE-VOTE | PRE-VOTE | VOTE | POST VOTE | PRE-VOTE | PRE-VOTE | VOTE | POST VOTE
| Hire/Appoint Vote Staff | 30 day deadline | Full Month or as advised by FN | Appeal Period | Hire/Appoint Vote Staff (if appl.) | 30 day deadline | Full Month or as advised by FN | Appeal Period
| Train Vote Staff | Notice of Vote |  | 10 day to submit | Train Vote Staff (if appl.) | Notice of Vote |  | 10 day to submit
| Prep for deadlines | Post List |  | 14 day to decide | Prep for deadlines | Post List |  | 14 day to decide
|  | Mail Outs |  |  |  | Mail Outs
|  | Info Session |  | *60 day post vote activities |  | Info Session |  | *60 day post vote activities

## SEPT 2021 - FEB 2022 2nd Vote
JULY 2021 | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | JANUARY 2022 | FEBRUARY | MARCH | APRIL
Someone looking at holding just a 2nd vote during this new timeframe would consider these timelines
2nd VOTE
PRE-VOTE | PRE-VOTE | VOTE | POST VOTE
Hire/Appoint Vote Staff (if appl.) | 30 day deadline | Full Month or as advised by FN | Appeal Period
Train Vote Staff (if appl.) | Notice of Vote |  | 10 day to submit
Prep for deadlines | Post List |  | 14 day to decide
Mail Outs
| Info Session |  | *60 day post vote activities
2nd VOTE
| PRE-VOTE | PRE-VOTE | VOTE | POST VOTE
| Hire/Appoint Vote Staff (if appl.) | 30 day deadline | Full Month or as advised by FN | Appeal Period
| Train Vote Staff (if appl.) | Notice of Vote |  | 10 day to submit
| Prep for deadlines | Post List |  | 14 day to decide
Mail Outs
|  | Info Session |  | *60 day post vote activities
2nd VOTE
|  | PRE-VOTE | PRE-VOTE | VOTE | POST VOTE
|  | Hire/Appoint Vote Staff (if appl.) | 30 day deadline | Full Month or as advised by FN | Appeal Period
|  | Train Vote Staff (if appl.) | Notice of Vote |  | 10 day to submit
|  | Prep for deadlines | Post List |  | 14 day to decide
Mail Outs
|  |  | Info Session |  | *60 day post vote activities
2nd VOTE
|  |  | PRE-VOTE | PRE-VOTE | VOTE | POST VOTE
|  |  | Hire/Appoint Vote Staff (if appl.) | 30 day deadline | Full Month or as advised by FN | Appeal Period
|  |  | Train Vote Staff (if appl.) | Notice of Vote |  | 10 day to submit
|  |  | Prep for deadlines | Post List |  | 14 day to decide
Mail Outs
|  |  |  | Info Session |  | *60 day post vote activities
2nd VOTE
|  |  |  | PRE-VOTE | PRE-VOTE | VOTE | POST VOTE
|  |  |  | Hire/Appoint Vote Staff (if appl.) | 30 day deadline | Full Month or as advised by FN | Appeal Period
|  |  |  | Train Vote Staff (if appl.) | Notice of Vote |  | 10 day to submit
|  |  |  | Prep for deadlines | Post List |  | 14 day to decide
Mail Outs
[5 empty] | Info Session |  | *60 day post vote activities
2nd VOTE
[5 empty] | PRE-VOTE | PRE-VOTE | VOTE | POST VOTE
[5 empty] | Hire/Appoint Vote Staff (if appl.) | 30 day deadline | Full Month or as advised by FN | Appeal Period
[5 empty] | Train Vote Staff (if appl.) | Notice of Vote |  | 10 day to submit
[5 empty] | Prep for deadlines | Post List |  | 14 day to decide
Mail Outs
[6 empty] | Info Session |  | *60 day post vote activities